## Tabelle1
Priority | Task | % Finished | Version | Bemerkung
1 | Movement
1.1 | Movement: Walk left | 100% | v0.0.5
1.2 | Movement: Walk right | 100% | v0.0.5
1.3 | Movement: Jump | 100% | v0.0.5
1.4 | Movement: Run left | 100% | v0.0.5
1.5 | Movement: Run right | 100% | v0.0.5
1.6 | Movement: Double Jump | 100% | v0.0.5
1.7 | Movement: Wall Jump | 100% | v0.0.6
1.8 | Movement: Dash | 100% | v0.0.6
2 | Combat and Cards
2.1 | Combat: Meele hit | 100% | v0.0.9
2.2 | Combat: Meele hit collision | 100% | v0.0.9
2.3 | Combat: Ranged Projectiles | 100% | v0.0.9
2.4 | Combat: Magic Projectiles | 50%
2.5 | Combat: Horizontal / Vertical hits | 50%
2.6 | Cards: Cards functionality
3 | Character
3.1 | Character: State-Machine | 100% | v0.0.6
3.2 | Character: Inventory System | 100% | v0.0.11
3.3 | Character: Stats
3.4 | Character: Exp/LVL-up-System
3.5 | Character: Permadeath
3.6 | Character: Multiple Characters
3.7 | Characterclass: Warrior
3.8 | Characterclass: Mage
3.9 | Characterclass: Rouge
4 | Combat
4.1 | Combat: Move set functionality
4.2 | Combat: Combo functionality
5 | HQ
5.1 | HQ: Main-Room
5.2 | HQ: Buildings
5.3 | HQ: Vendors(NPC)
5.4 | HQ: Talentsystem for Buildings
5.5 | HQ: Unlockables functionality
6 | Character
6.1 | Character: Card-Talent-/LVL-System
7 | Cards
7.1 | Cards: Rarity functionality | 50%
7.2 | Cards: Loot functionality
7.3 | Cards: Weapon Cards | 50%
7.4 | Cards: Gamemodifier Cards
7.5 | Cards: Skills Cards
7.6 | Cards: Magic Cards
7.7 | Cards: Potion Cards
8 | Enemies
8.1 | Enemy Move: Move
8.2 | Enemy Move: Patrol
8.3 | Enemy Move: Chase Player
8.4 | Enemy Move: Attack
8.5 | Enemy Move: Death
9 | Boss
9.1 | Boss: Move
9.2 | Boss: Chase Player
9.3 | Boss: Attack
9.4 | Boss: States
9.5 | Boss: Skills
10 | Story Mode
10.1 | SM: Stage 1 Room Design
10.2 | SM: Stage 1 Enemies Strategy Design
10.3 | SM: Stage 1 Items Design
10.4 | SM: Stage 1 Goals Design
10.5 | SM: Stage 2 Room Design
10.6 | SM: Stage 2 Enemies Strategy Design
10.7 | SM: Stage 2 Items Design
10.8 | SM: Stage 2 Goals Design
10.9 | SM: Stage 3 Room Design
10.10 | SM: Stage 3 Enemies Strategy Design
10.11 | SM: Stage 3 Items Design
10.12 | SM: Stage 3 Goals Design
11 | Endless-Mode
11.1 | EM: Procedural Generated Rooms
11.2 | EM: Procedural Generated Enemy and Object Spawns
11.3 | EM: Special Rooms
NR | BUG | % Finished | Version | Bemerkung
1 | While SHIFT-Running and attacking, the SHIFT-Speed is gone, and character slows down. Run speed needs to stay the same while attacking | 0% |  | Found in Version 0.0.9